## Sheet1
Task Type | Task | Jira Link | Done | Todo | Assignee | What do I need to provide?
Automation | Automation Adoption for Raptor Applications - perdformanceApp | http://jira.verifone.com:8080/browse/CORSQADEV-427 | Complete code changing, testing on P400 device. Code checked in to automation_phase1 branch. | Help Ofer with the package or anything needed for the test. | Robert
| Automation Adoption for Raptor Applications - ethSqa | http://jira.verifone.com:8080/browse/CORSQADEV-428 | Complete code changing, testing on P400 device. Code checked in to automation_phase1 branch. | Help Ofer with the package or anything needed for the test. | Ofer
| Automation Adoption for Raptor Applications - svc_netloader | http://jira.verifone.com:8080/browse/CORSQADEV-429 | This is on hold for automation phase 1
| Automation Adoption for Raptor Applications - vfimodem | http://jira.verifone.com:8080/browse/CORSQADEV-430 | Complete code changing. Code checked in to automation_phase1 branch. Updated .cproject | Need to work on job config file and test on a certain devices. | Robert | What is the protensial?
| Automation Adoption for Raptor Applications - svcmsrApp | http://jira.verifone.com:8080/browse/CORSQADEV-436 | Complete code changing. Code checked in to automation_phase1 branch. Updated .cproject | Need to work on job config file and test on a certain devices. | Robert | High priority
| Automation Adoption for Raptor Applications - vfiltpApp | http://jira.verifone.com:8080/browse/CORSQADEV-435 | Complete code changing. Code checked in to automation_phase1 branch. Updated .cproject | Need to work on job config file and test on a certain devices. | Robert
HWQA | Wifi Test for HWQA | http://jira.verifone.com:8080/browse/CORSQADEV-470 | Done. |  | Ofer
| 3g/4g Test for HWQA | http://jira.verifone.com:8080/browse/CORSQADEV-361 | Done. |  | Ofer
ADK | Add Samsung Pay Test to ADK acceptance test for Raptor | http://jira.verifone.com:8080/browse/ASQD-244 | Clean code project to test MST. | Build ADK acceptance test and bring the changes for MST. Test on Raptor devices. | Lovejit | Local Clean code for testing the MST. ADK projects souce files.
| JavaScript Test Framework for ADK |  |  | Look into the JavaScript test framework and make it run. Check the limitations of the Duktape scripts we support on ADK and see how we test it with any existing test framework. | Lovejit |  | Alex
ECR | Feedback for svc_ecr | http://jira.verifone.com:8080/browse/CORSQADEV-485 | Updated the ticket. |  | Yonatan
| Feedback for svc_ecr about life cycle | http://jira.verifone.com:8080/browse/CORSQADEV-483 | Updated the ticket. |  | Yonatan
| Platform Info test needed for ECR | http://jira.verifone.com:8080/browse/CORSQADEV-109 http://jira.verifone.com:8080/browse/CORSQADEV-122 | ON HOLD - for ECR we don't have platform info application yet |  | Yonatan
| Feedback for kbdsqa | http://jira.verifone.com:8080/browse/CORSQADEV-42 | Updated the ticket. |  | Yonatan
| Feedback for vfimodem | http://jira.verifone.com:8080/browse/CORSQADEV-46 | Not started yet. |  | Yonatan
| Feedback for svcLed | http://jira.verifone.com:8080/browse/CORSQADEV-104 | Updated the ticket. |  | Yonatan
| Clarifications on kbdSqa | http://jira.verifone.com:8080/browse/CORSQADEV-111 | Not started yet. |  | Yonatan
| Clarifications of printer test app | http://jira.verifone.com:8080/browse/CORSQADEV-130 | Not started yet. |  | Yonatan
Ux410 | Feedback on Platform Info | http://jira.verifone.com:8080/browse/CORSQADEV-283 | on hold
VOSCORDEV issues | Improvement for IOP test | http://jira.verifone.com:8080/browse/CORSQADEV-187
| Add summary for cycle test | http://jira.verifone.com:8080/browse/CORSQADEV-258
| Add barcode support in Acceptance | http://jira.verifone.com:8080/browse/CORSQADEV-343 | Done. Code in local
| Fix menu in Acceptance | http://jira.verifone.com:8080/browse/CORSQADEV-397
| Fix print test for SF | http://jira.verifone.com:8080/browse/CORSQADEV-420 | Done and released fix. | Need to close this.
VOSCOR issues | ON ANOTHER LIST